# Aurelius Capital Group – Quick Stand-Up Actions

Business / Real Estate (Screening discipline, deal standards, packaging)

Table of Contents

Overview	2

1) Business / Logistics (Ops, systems, contracts, reporting)	2

2) Business / Real Estate (Screening discipline, deal standards, packaging)	2

3) Sales Management (Recruiting, coaching, cadence, performance)	3

4) Communications (Collateral, messaging control, trust-building)	3

10-Day Feasibility	3

What’s realistic to finish in 10 days (MVP definition)	4

Green (highly doable):	4

Yellow (doable as MVP, but “final” depends on legal/tools):	4

Red (not fully controllable in 10 days):	4

Critical-path dependencies (what must happen first)	4

Bottom-line feasibility call	4

Your Mission, Should You Choose to Accept It	5

Business / Real Estate (Screening discipline, deal standards, packaging)	5

Role Mission (10-day MVP)	5

MVP Deliverables (what this person must produce)	5

A) Define what qualifies	5

Lock the Owner/Asset eligibility criteria (asset types, size bands, income/occupancy expectations, authority/objective requirements)	5

Build the red-flag list + “fast fail” rules aligned to screening stages	7

B) Standardize what “partner-ready” means	8

Define the minimum required data/doc standard before partner introduction	8

Expected Outcome (Definition of Done)	9

Create the Asset Brief template (2–3 pages) and the “Typical Deal Path” expectations one-pager	9

Asset Brief Template (2–3 pages) — Build Instructions (MVP)	9

Typical Deal Path One-Pager — Build Instructions (MVP)	10

C) Calibrate quality	10

Produce 3 example profiles: Strong / Borderline / Reject	10

D) Set role boundaries	11

Write the Originator-allowed vs ACG-only conversation boundary guide	11

Originator Allowed (what they can gather)	11

ACG-only (what originators must NOT do)	11

Add “safe language” snippets	11

Day 10 Acceptance Test for Role 2 (Biz/RE)	12

# Overview

- This Overview second contains a list of what everyone is responsible for at a high level.

  - You’ll see a clean, short-term (next 10 days) task list by role.

- 10-Day Feasibility: In case you were wondering about the feasibility of completing your task in 10-days, read this.

- If not, just skip to Your Mission, Should You Choose to Accept It. This contains:

Mission → Deliverables → How to build → Definition of Done → What ‘finished MVP’ looks like

## 1) Business / Logistics (Ops, systems, contracts, reporting)

- Stand up the operating system

  - Finalize the end-to-end stage-gate SOP (stages, pass/fail rules, required outputs, SLAs, handoffs).

- Build the infrastructure

  - Configure the CRM pipelines (Owners / Originators / Partners / Deals) with required fields, stages, and activity tracking.

  - Set up a secure doc intake/upload workflow (even if simple: structured folders + naming standards).

- Formalize relationships

  - Draft/complete the Originator Contractor Agreement + Program Rules (conduct, boundaries, non-circumvention, confidentiality).

  - Draft/complete the Partner Intro Terms (success fee trigger at close, confidentiality, non-circumvention, dispute handling).

  - Package Owner NDA / Mandate packet for consistent use.

- Make it measurable

  - Create the weekly metrics snapshot (pipeline counts, stage conversions, next actions, originator activity, partner status).

## 2) Business / Real Estate (Screening discipline, deal standards, packaging)

- Define what qualifies

  - Lock the Owner/Asset eligibility criteria (asset types, size bands, income/occupancy expectations, authority/objective requirements).

  - Build the red-flag list + “fast fail” rules aligned to screening stages.

- Standardize what “partner-ready” means

  - Define the minimum required data/doc standard before partner introduction.

  - Create the Asset Brief template (2–3 pages) and the “Typical Deal Path” expectations one-pager.

- Calibrate quality

  - Produce 3 example profiles: Strong / Borderline / Reject (for training and internal consistency).

- Set role boundaries

  - Write the Originator-allowed vs ACG-only conversation boundary guide (what originators can gather vs what stays with ACG).

## 3) Sales Management (Recruiting, coaching, cadence, performance)

- Build the originator channel

  - Create a target list + outreach sequence and run a recruiting funnel (25–50 targets).

  - Write the Originator Pitch (why join, how they’re supported, how they get paid, expectations).

- Operationalize execution

  - Produce the Originator Field Pack: call openers, voicemail, email templates, objection handling, “next step” closes.

  - Define the lead handling workflow (assignment rules, SLAs, recycle rules) and enforce it.

- Establish rhythm

  - Launch the weekly cadence: pipeline huddle agenda + stalled-deal recovery process + KPI accountability.

- Pilot the system

  - Onboard 2–3 pilot originators end-to-end to validate the workflow and refine scripts.

## 4) Communications (Collateral, messaging control, trust-building)

- Control the message

  - Create the Master Messaging & Compliance-Safe Language Guide (approved phrases, phrases to avoid, disclaimers).

- Build the “kits”

  - Produce the Owner Education Kit (plain-English explainer, process steps, timeline, FAQs).

  - Produce the Originator Program One-Pager (what it is, who it’s for, benefits, expectations).

  - Produce the Partner Onboarding/Intro Pack (ACG overview + how ACG screens/packages + intro protocol).

- Standardize outreach

  - Draft and store email templates for: owner intro, NDA send, intake follow-up, partner intro, originator recruiting.

- Make it easy to distribute

  - Package everything into a clean version-controlled folder structure (one “source of truth” kit set).

# 10-Day Feasibility

10 days is feasible for an “MVP operating system” (ready to run pilot originators + start partner/owner conversations) because a lot of the “heavy” artifacts already exist and mostly need packaging, tightening, and wiring into a workflow(e.g., Screening SOP, fee schedule, partner onboarding pack, owner mandate + NDA, originator comp framework, partner emails).

Where 10 days becomes not feasible is if “complete” means production-grade + attorney-reviewed + fully automated + fully validated with market response. Some outcomes are inherently time-uncertain (partner replies, owner responsiveness, originator recruiting conversion).

## What’s realistic to finish in 10 days (MVP definition)

### Green (highly doable):

- Stage-gate SOP (you already have the 5-stage screening backbone; this is mainly tightening pass/fail, outputs, SLAs, handoffs).

- Eligibility criteria + fast-fail rules + partner-ready minimum data (directly derived from existing SOP and onboarding materials).

- Asset Brief template + “Typical Deal Path” one-pager (straightforward to draft from your deck + SOP + onboarding pack).

- Owner education kit / FAQs (you already have an Owner Q&A that can be packaged into a clean kit).

- Email templates (partner intro + follow-up already drafted; others can be patterned off these).

- Weekly metrics snapshot (simple dashboard/report once CRM stages are defined).

### Yellow (doable as MVP, but “final” depends on legal/tools):

- Originator Contractor Agreement + Program Rules: you can draft quickly, but “finalize” ideally includes counsel review.

- Partner Intro Terms: same—draftable fast, but legal polish may extend beyond 10 days.

- Master Messaging & Compliance-Safe Language Guide: you can create an internal “approved language + forbidden language + disclaimers” guide quickly, but true compliance sign-off is a legal function (especially if you’re operating across jurisdictions). Your existing “what we do / do not do” language is a strong base.

- CRM + secure doc intake: feasible if you accept an “80/20” setup (pipelines + required fields + structured folder system). If you also want automation, integrations, and perfect data governance, that’s beyond 10 days.

### Red (not fully controllable in 10 days):

- Recruiting funnel results (25–50 targets can be outreached; conversion to 2–3 onboarded originators depends on response rates).

- Pilot outcomes (you can start pilots and validate workflow, but getting clean cycle-time data + closed-loop learning typically takes longer than 10 days).

## Critical-path dependencies (what must happen first)

- Stage-gate SOP + definitions (what “pass” means, required outputs at each stage).

- CRM pipelines + required fields (so every activity has a home + reporting works).

- Doc intake + naming standards (so packaging doesn’t collapse into chaos).

- Owner mandate/NDA packet + partner intro terms (so you can safely move deals).

- Originator boundaries + field pack (so originators don’t create regulatory/messaging risk).

## Bottom-line feasibility call

- If the goal is “ready to operate + run 2–3 originator pilots + begin selective partner/owner conversations”: Yes, feasible in 10 days, assuming focused execution and using the existing assets you already have.

- If the goal is “fully institutionalized, legally finalized across jurisdictions, deeply automated, and validated with measurable recruiting/partner conversion”: Not feasible in 10 days—but you can still hit an MVP that’s operationally tight and de-risks the next 30–60 days.

# Your Mission, Should You Choose to Accept It

## Business / Real Estate (Screening discipline, deal standards, packaging)

### Role Mission (10-day MVP)

By Day 10, Biz/RE makes ACG credible and consistent: every opportunity is screened the same way, fast-failed quickly when it should be, and packaged into a partner-ready brief that partners can act on without back-and-forth.

#### “Finished MVP” looks like this (vision)

- An originator submits an owner lead → Biz/RE can qualify or fast-fail in 15–30 minutes using a standard checklist.

- A “Pass” means something precise: the deal has the minimum data + docs and a clean story.

- A partner intro happens only when the deal is truly partner-ready: Asset Brief + Data Room + Deal Thesis + Clear asks are complete.

- Originators stay in their lane. Biz/RE protects quality and compliance by controlling what’s asked, promised, and interpreted.

### MVP Deliverables (what this person must produce)

- Owner/Asset Eligibility Criteria (a one-page matrix + CRM checklist)

- Red Flags + Fast-Fail Rules (a one-page list aligned to stages)

- Partner-Ready Standard (minimum data/doc checklist + “missing items” rules)

- Asset Brief Template (2–3 pages) + Typical Deal Path One-Pager

- 3 Example Profiles (Strong / Borderline / Reject) using the templates

- Conversation Boundary Guide (Originator-allowed vs ACG-only)

## A) Define what qualifies

### Lock the Owner/Asset eligibility criteria (asset types, size bands, income/occupancy expectations, authority/objective requirements)

#### Build Instructions (MVP)

Create a 1-page Eligibility Matrix with “Accept / Maybe / Reject” thresholds. Keep it simple enough to train originators, strict enough to protect partner time.

#### 1) Asset Type Fit (set your MVP lane)

Define exactly which asset types are in-bounds for MVP. Example structure:

- In-Bounds (MVP focus): (e.g., multifamily, self-storage, industrial, retail centers, etc.)

- Conditional: (e.g., land, hospitality, special-use, development)

- Out-of-Bounds: (anything you are not packaging in MVP)

MVP rule: fewer asset types = faster screening discipline.

#### 2) Size Bands (choose ranges partners actually care about)

Pick two bands:

- Sweet Spot: where you want most deals to land

- Minimum Floor: below which you generally don’t pursue (unless strategic)

You can express size as:

- Estimated value range (ballpark)

- NOI range

- Units / square footage

- Loan size (if relevant)

#### 3) Performance Expectations (quick indicators)

Define minimum expectations for:

- Occupancy / utilization (if stabilized asset)

- Income documentation available (rent roll, T12/operating statement)

- Stability: how many months of consistent performance

#### 4) Owner Requirements (authority + objective)

Define screening “must haves”:

- Authority: “Is the person we’re speaking to able to decide or sign?”

- Objective: clear intent (sell / refinance / recap / raise / restructure)

- Timeline: immediate / 30–90 / 90+

- Motivation clarity: why now?

#### 5) Turn it into a CRM checklist

Your eligibility matrix must become:

- A checkbox/dropdown set in the Deal record

- A Pass/Fail field with reason codes

#### Expected Outcome (Definition of Done)

✅ One-page Eligibility Matrix that:

- States in-bounds asset types

- Has size bands (sweet spot + minimum floor)

- Defines minimum performance/documentation expectations

- Includes owner authority + objective requirements

- Can be used to decide: Pass / Park / Reject quickly

#### “Finished MVP” looks like

A new lead arrives and within 30 minutes Biz/RE can say:

- “This is in our MVP lane / not in our lane”

- “This is partner-viable / not partner-viable”

- “Here’s what’s missing to proceed”

### Build the red-flag list + “fast fail” rules aligned to screening stages

#### Build Instructions (MVP)

Create a Fast-Fail Sheet with two categories:

#### Category 1: “Instant Reject” (no further work)

Examples of what typically belongs here:

- Owner can’t verify ownership or authority

- Refuses NDA but wants sensitive guidance/data

- Material inconsistencies in basic facts (address, ownership, asset type)

- Legal/ethical red flags (fraud indicators, unwillingness to provide basic proof)

- Asset type is out-of-bounds for MVP

#### Category 2: “Park Until Fixed”

Examples:

- Missing basic docs but owner is cooperative

- Timing too far out (e.g., 6–12 months)

- Financials unclear but can be clarified with T12/rent roll

- Cap stack complexity that requires partner consult later

#### Align to stages

Map fast-fails to where they occur:

- Pre-Screen fast-fails: identity, authority, asset in-bounds, basic objective, baseline data

- Screen/Validate fast-fails: inability to validate income/occupancy, title/ownership issues, critical missing docs, contradictory info

- Packaging fast-fails: owner won’t cooperate with packaging, refuses required disclosures, can’t produce core docs

#### Expected Outcome (Definition of Done)

✅ One-page red-flag list with:

- “Instant Reject” rules

- “Park until fixed” rules

- Stage mapping (where each fast-fail triggers)

- Reason codes that match the CRM (so reporting is clean)

#### “Finished MVP” looks like

Team stops wasting cycles:

- Bad deals get rejected politely fast

- “Maybe later” deals get parked with a clear re-entry trigger

## B) Standardize what “partner-ready” means

### Define the minimum required data/doc standard before partner introduction

#### Build Instructions (MVP)

Create a Partner-Ready Checklist with three layers:

#### Layer 1: Minimum Viable Data (no exceptions)

- Asset address + description

- Asset type + basic specs (units/SF, year built, condition notes)

- Ownership/entity name (or proof path)

- Owner objective + timeline

- High-level financial snapshot (NOI/revenue estimate range is fine if sourced)

- Known issues (vacancy, deferred maintenance, liens—if disclosed)

#### Layer 2: Minimum Viable Docs (target list)

For income-producing assets, MVP docs commonly include:

- Rent roll (or occupancy summary)

- Trailing 12 / operating statement (even if owner-generated initially)

- Tax bill / assessment (baseline)

- Photos / basic condition notes

- Entity/ownership verification (as available)

If a doc is missing, you need a rule:

- Either “partner-ready cannot proceed without it”

- Or “proceed if X substitute exists” (e.g., bank statements in lieu of T12)

#### Layer 3: Deal Story & Ask (required narrative)

Every partner intro must include:

- What the owner wants (one sentence)

- Why it makes sense (one paragraph)

- What ACG is asking the partner to do (clear action request)

- The “next step” call ask (15–30 min review call, etc.)

### Expected Outcome (Definition of Done)

✅ A Partner-Ready Checklist that:

- Defines “minimum viable” data + docs

- Defines substitutes and exceptions

- Defines intro-ready narrative requirements

- Becomes a gating checklist inside CRM

#### “Finished MVP” looks like

Partners get intros that feel professional:

- Fewer follow-ups

- Faster “yes/no”

- More trust in ACG packaging discipline

### Create the Asset Brief template (2–3 pages) and the “Typical Deal Path” expectations one-pager

### Asset Brief Template (2–3 pages) — Build Instructions (MVP)

Design for speed and clarity. Target: 10–20 minutes to assemble once data exists.

Page 1: Executive Snapshot

- Deal ID + asset name/location

- Owner objective + timeline

- Asset overview (type, size, highlights)

- Financial headline numbers (revenue/NOI/occupancy; clearly labeled as “owner-provided” if so)

- ACG view: “why this is worth a look” (3 bullets)

- The ask: “What we want the partner to do next” (1–2 bullets)

Page 2: Asset & Performance Detail

- Unit/SF mix or tenant overview (as applicable)

- Occupancy trend (simple)

- Expenses snapshot (high-level)

- Capex/deferred maintenance notes

- Market context (2–4 bullets, no deep research needed in MVP)

Page 3 (optional): Risks + Process + Attachments

- Key risks / unknowns (bullet list)

- Open questions (what partner should evaluate)

- Data room contents list (what’s included)

- Contact protocol (who communicates with owner and how)

### Typical Deal Path One-Pager — Build Instructions (MVP)

This is for owner alignment and partner clarity. Include:

- The stages (intake → pre-screen → validate → package → partner intro → partner process → close)

- Typical timeline ranges (best case / normal)

- What the owner must provide (docs + responsiveness expectations)

- What ACG does vs what the partner does

- Important disclaimers (plain-English)

#### Expected Outcome (Definition of Done)

✅ Two polished templates exist:

- Asset Brief (2–3 pages) in Doc/PDF format

- Typical Deal Path one-pager
…and both are stored as the single source of truth for packaging.

#### “Finished MVP” looks like

Any team member can pick up the templates and produce consistent outputs that “look like ACG.”

## C) Calibrate quality

### Produce 3 example profiles: Strong / Borderline / Reject

#### Build Instructions (MVP)

Using the new templates, create 3 sample deal profiles (fictionalized is fine, or sanitized real patterns):

#### 1) Strong Example

- Clean authority + clear objective

- Docs mostly available

- Metrics fall in the sweet spot

- Easy partner-ready story

#### 2) Borderline Example

- Some missing docs, but cooperative owner

- Slightly outside sweet spot (size, occupancy, condition)

- Shows how to “Park until fixed” OR how to proceed with conditions

#### 3) Reject Example

- Triggers fast-fail rules

- Demonstrates the polite rejection language + CRM coding

Each example must include:

- Eligibility matrix result

- Fast-fail / pass rationale

- Partner-ready checklist status

- Asset Brief (even if shorter)

#### Expected Outcome (Definition of Done)

✅ Three examples exist that:

- Teach the standards

- Make gray areas obvious

- Can be used to onboard originators + internal team

#### “Finished MVP” looks like

When someone argues “this seems fine,” you can point to examples and say:

- “This is Borderline; it needs X”

- “This is Reject because it triggers rule Y”

## D) Set role boundaries

### Write the Originator-allowed vs ACG-only conversation boundary guide

#### Build Instructions (MVP)

Create a 1–2 page boundary guide with two columns:

### Originator Allowed (what they can gather)

- Basic owner info + best contact method

- Basic asset description (type, address, size/unit count)

- Owner objective + timeline (high-level)

- Whether docs exist (yes/no) and willingness to share under NDA

- Permission to send NDA + intro packet

- Scheduling a call with ACG

### ACG-only (what originators must NOT do)

- Discuss pricing/fees in detail beyond approved language

- Make promises about outcomes, partners, timelines, or approvals

- Interpret financials, underwriting, valuation, token terms, securities-like language

- Negotiate terms

- Request sensitive documents without the approved intake process

- Communicate “partner names” prematurely or attempt direct partner coordination

### Add “safe language” snippets

Include a few approved phrases originators can use:

- “ACG will review and confirm fit after NDA and basic intake.”

- “We don’t make commitments until the core team validates the package.”

- “We’ll introduce you to the right regulated partner if it qualifies.”

#### Expected Outcome (Definition of Done)

✅ Boundary guide exists and is enforced:

- Included in Originator Field Pack

- Signed acknowledgment (checkbox in CRM or as part of Program Rules)

#### “Finished MVP” looks like

Originators act as disciplined scouts, not closers:

- They gather just enough to qualify

- They protect the brand and keep ACG in control of partner-facing accuracy

## Day 10 Acceptance Test for Role 2 (Biz/RE)

If all are “yes,” this role’s MVP is complete:

- Can we decide Pass/Park/Reject in <30 minutes using a standard matrix?

- Do we have written fast-fail rules and stage alignment?

- Do we have a partner-ready checklist that gates intros?

- Can we produce a clean 2–3 page Asset Brief within 1 hour once docs exist?

- Do we have Strong/Borderline/Reject examples for training?

- Do originators have a clear boundary guide with safe language?