# Aurelius Capital Group – Quick Stand-Up Actions by Role

Table of Contents

Overview	3

1) Business / Logistics (Ops, systems, contracts, reporting)	3

2) Business / Real Estate (Screening discipline, deal standards, packaging)	3

3) Sales Management (Recruiting, coaching, cadence, performance)	4

4) Communications (Collateral, messaging control, trust-building)	4

10-Day Feasibility	4

What’s realistic to finish in 10 days (MVP definition)	5

Green (highly doable):	5

Yellow (doable as MVP, but “final” depends on legal/tools):	5

Red (not fully controllable in 10 days):	5

Critical-path dependencies (what must happen first)	5

Bottom-line feasibility call	5

Your Mission, Should You Choose to Accept It	6

Business / Logistics (Ops, systems, contracts, reporting)	6

Role Mission (10-day MVP)	6

MVP Deliverables (what this person must produce)	6

A) Stand up the operating system	6

Finalize the end-to-end stage-gate SOP (stages, pass/fail rules, required outputs, SLAs, handoffs)	6

B) Build the infrastructure	8

Configure the CRM pipelines (Owners / Originators / Partners / Deals) with required fields, stages, and activity tracking	8

Set up a secure doc intake/upload workflow (structured folders + naming standards)	9

C) Formalize relationships	10

Draft/complete Originator Contractor Agreement + Program Rules	10

Draft/complete Partner Intro Terms	11

Package Owner NDA / Mandate packet for consistent use	11

D) Make it measurable	11

Create the weekly metrics snapshot	11

Quick “Day 10 Acceptance Test”	12

Business / Real Estate (Screening discipline, deal standards, packaging)	13

Role Mission (10-day MVP)	13

MVP Deliverables (what this person must produce)	13

A) Define what qualifies	13

Lock the Owner/Asset eligibility criteria (asset types, size bands, income/occupancy expectations, authority/objective requirements)	13

Build the red-flag list + “fast fail” rules aligned to screening stages	15

B) Standardize what “partner-ready” means	16

Define the minimum required data/doc standard before partner introduction	16

Expected Outcome (Definition of Done)	17

Create the Asset Brief template (2–3 pages) and the “Typical Deal Path” expectations one-pager	17

Asset Brief Template (2–3 pages) — Build Instructions (MVP)	17

Typical Deal Path One-Pager — Build Instructions (MVP)	18

C) Calibrate quality	18

Produce 3 example profiles: Strong / Borderline / Reject	18

D) Set role boundaries	19

Write the Originator-allowed vs ACG-only conversation boundary guide	19

Originator Allowed (what they can gather)	19

ACG-only (what originators must NOT do)	19

Add “safe language” snippets	19

Day 10 Acceptance Test for Role 2 (Biz/RE)	20

Sales Management (Recruiting, coaching, cadence, performance)	21

Role Mission (10-day MVP)	21

MVP Deliverables (what this person must produce)	21

A) Build the originator channel	21

Create a target list + outreach sequence and run a recruiting funnel (25–50 targets)	21

Write the Originator Pitch (why join, how supported, how paid, expectations)	23

B) Operationalize execution	24

Produce the Originator Field Pack	24

Define the lead handling workflow (assignment rules, SLAs, recycle rules) and enforce it	25

C) Establish rhythm	26

Launch the weekly cadence: pipeline huddle agenda + stalled-deal recovery + KPI accountability	26

D) Pilot the system	27

Onboard 2–3 pilot originators end-to-end to validate the workflow and refine scripts	27

Day 10 Acceptance Test for Role 3 (Sales Management)	28

Communications (Collateral, messaging control, trust-building)	29

Role Mission (10-day MVP)	29

MVP Deliverables (what this person must produce)	29

A) Control the message	29

Create the Master Messaging & Compliance-Safe Language Guide	29

B) Build the kits	31

C) Standardize outreach	33

Draft and store email templates	33

Build Instructions (MVP)	33

Minimum set (MVP = 5 templates)	33

D) Make it easy to distribute	33

Package everything into a clean version-controlled folder structure (one “source of truth” kit set)	33

Folder structure (recommended MVP)	34

Versioning standard (simple)	34

Governance rules (MVP must-have)	34

Day 10 Acceptance Test for Role 4 (Communications)	34

# Overview

- This Overview second contains a list of what everyone is responsible for at a high level.

  - You’ll see a clean, short-term (next 10 days) task list by role.

- 10-Day Feasibility: In case you were wondering about the feasibility of completing your task in 10-days, read this.

- If not, just skip to Your Mission, Should You Choose to Accept It. This contains:

Mission → Deliverables → How to build → Definition of Done → What ‘finished MVP’ looks like

## 1) Business / Logistics (Ops, systems, contracts, reporting)

- Stand up the operating system

  - Finalize the end-to-end stage-gate SOP (stages, pass/fail rules, required outputs, SLAs, handoffs).

- Build the infrastructure

  - Configure the CRM pipelines (Owners / Originators / Partners / Deals) with required fields, stages, and activity tracking.

  - Set up a secure doc intake/upload workflow (even if simple: structured folders + naming standards).

- Formalize relationships

  - Draft/complete the Originator Contractor Agreement + Program Rules (conduct, boundaries, non-circumvention, confidentiality).

  - Draft/complete the Partner Intro Terms (success fee trigger at close, confidentiality, non-circumvention, dispute handling).

  - Package Owner NDA / Mandate packet for consistent use.

- Make it measurable

  - Create the weekly metrics snapshot (pipeline counts, stage conversions, next actions, originator activity, partner status).

## 2) Business / Real Estate (Screening discipline, deal standards, packaging)

- Define what qualifies

  - Lock the Owner/Asset eligibility criteria (asset types, size bands, income/occupancy expectations, authority/objective requirements).

  - Build the red-flag list + “fast fail” rules aligned to screening stages.

- Standardize what “partner-ready” means

  - Define the minimum required data/doc standard before partner introduction.

  - Create the Asset Brief template (2–3 pages) and the “Typical Deal Path” expectations one-pager.

- Calibrate quality

  - Produce 3 example profiles: Strong / Borderline / Reject (for training and internal consistency).

- Set role boundaries

  - Write the Originator-allowed vs ACG-only conversation boundary guide (what originators can gather vs what stays with ACG).

## 3) Sales Management (Recruiting, coaching, cadence, performance)

- Build the originator channel

  - Create a target list + outreach sequence and run a recruiting funnel (25–50 targets).

  - Write the Originator Pitch (why join, how they’re supported, how they get paid, expectations).

- Operationalize execution

  - Produce the Originator Field Pack: call openers, voicemail, email templates, objection handling, “next step” closes.

  - Define the lead handling workflow (assignment rules, SLAs, recycle rules) and enforce it.

- Establish rhythm

  - Launch the weekly cadence: pipeline huddle agenda + stalled-deal recovery process + KPI accountability.

- Pilot the system

  - Onboard 2–3 pilot originators end-to-end to validate the workflow and refine scripts.

## 4) Communications (Collateral, messaging control, trust-building)

- Control the message

  - Create the Master Messaging & Compliance-Safe Language Guide (approved phrases, phrases to avoid, disclaimers).

- Build the “kits”

  - Produce the Owner Education Kit (plain-English explainer, process steps, timeline, FAQs).

  - Produce the Originator Program One-Pager (what it is, who it’s for, benefits, expectations).

  - Produce the Partner Onboarding/Intro Pack (ACG overview + how ACG screens/packages + intro protocol).

- Standardize outreach

  - Draft and store email templates for: owner intro, NDA send, intake follow-up, partner intro, originator recruiting.

- Make it easy to distribute

  - Package everything into a clean version-controlled folder structure (one “source of truth” kit set).

# 10-Day Feasibility

10 days is feasible for an “MVP operating system” (ready to run pilot originators + start partner/owner conversations) because a lot of the “heavy” artifacts already exist and mostly need packaging, tightening, and wiring into a workflow(e.g., Screening SOP, fee schedule, partner onboarding pack, owner mandate + NDA, originator comp framework, partner emails).

Where 10 days becomes not feasible is if “complete” means production-grade + attorney-reviewed + fully automated + fully validated with market response. Some outcomes are inherently time-uncertain (partner replies, owner responsiveness, originator recruiting conversion).

## What’s realistic to finish in 10 days (MVP definition)

### Green (highly doable):

- Stage-gate SOP (you already have the 5-stage screening backbone; this is mainly tightening pass/fail, outputs, SLAs, handoffs).

- Eligibility criteria + fast-fail rules + partner-ready minimum data (directly derived from existing SOP and onboarding materials).

- Asset Brief template + “Typical Deal Path” one-pager (straightforward to draft from your deck + SOP + onboarding pack).

- Owner education kit / FAQs (you already have an Owner Q&A that can be packaged into a clean kit).

- Email templates (partner intro + follow-up already drafted; others can be patterned off these).

- Weekly metrics snapshot (simple dashboard/report once CRM stages are defined).

### Yellow (doable as MVP, but “final” depends on legal/tools):

- Originator Contractor Agreement + Program Rules: you can draft quickly, but “finalize” ideally includes counsel review.

- Partner Intro Terms: same—draftable fast, but legal polish may extend beyond 10 days.

- Master Messaging & Compliance-Safe Language Guide: you can create an internal “approved language + forbidden language + disclaimers” guide quickly, but true compliance sign-off is a legal function (especially if you’re operating across jurisdictions). Your existing “what we do / do not do” language is a strong base.

- CRM + secure doc intake: feasible if you accept an “80/20” setup (pipelines + required fields + structured folder system). If you also want automation, integrations, and perfect data governance, that’s beyond 10 days.

### Red (not fully controllable in 10 days):

- Recruiting funnel results (25–50 targets can be outreached; conversion to 2–3 onboarded originators depends on response rates).

- Pilot outcomes (you can start pilots and validate workflow, but getting clean cycle-time data + closed-loop learning typically takes longer than 10 days).

## Critical-path dependencies (what must happen first)

- Stage-gate SOP + definitions (what “pass” means, required outputs at each stage).

- CRM pipelines + required fields (so every activity has a home + reporting works).

- Doc intake + naming standards (so packaging doesn’t collapse into chaos).

- Owner mandate/NDA packet + partner intro terms (so you can safely move deals).

- Originator boundaries + field pack (so originators don’t create regulatory/messaging risk).

## Bottom-line feasibility call

- If the goal is “ready to operate + run 2–3 originator pilots + begin selective partner/owner conversations”: Yes, feasible in 10 days, assuming focused execution and using the existing assets you already have.

- If the goal is “fully institutionalized, legally finalized across jurisdictions, deeply automated, and validated with measurable recruiting/partner conversion”: Not feasible in 10 days—but you can still hit an MVP that’s operationally tight and de-risks the next 30–60 days.

# Your Mission, Should You Choose to Accept It

## Business / Logistics (Ops, systems, contracts, reporting)

### Role Mission (10-day MVP)

By Day 10, Ops makes ACG runnable: every lead can be tracked, screened, documented, contracted, introduced, and reported the same way every time—with clear handoffs and minimal ambiguity.

#### “Finished MVP” looks like this (vision)

- A new owner lead comes in → it enters the system the same day, with a Deal ID, assigned owner, next action, and required doc checklist.

- The team can answer at any moment:

  - “How many deals are in each stage?”

  - “Which originators are producing?”

  - “What’s blocked and why?”

  - “Which partners are active and responsive?”

- Nobody sends random attachments or loses versions—everything is in the same folder structure, named the same way.

- No one “freelances” language: templates + terms + SOP enforce consistency.

### MVP Deliverables (what this person must produce)

- Stage-Gate SOP (end-to-end)

- CRM pipelines + fields + rules

- Secure doc intake + naming/folder standards

- Contract pack (Originator, Partner Intro Terms, Owner NDA/Mandate packet) + signature workflow

- Weekly metrics snapshot + meeting rhythm

## A) Stand up the operating system

### Finalize the end-to-end stage-gate SOP (stages, pass/fail rules, required outputs, SLAs, handoffs)

#### Build Instructions (MVP)

Create a 6–10 page SOP that includes:

#### 1) The stages (your “single source of truth” flow)

Use a simple stage list like:

- Lead Intake

- Pre-Screen (Fast Fail)

- Screen & Validate (Partner-Ready Standard)

- Package (Asset Brief + data room complete)

- Partner Introduction

- Partner Process + Close Tracking

- Closed / Lost / Parked

(You can name them differently—what matters is clear entry/exit criteria.)

#### 2) For EACH stage, define 5 things:

- Entry criteria: what must be true to enter this stage

- Required actions: what work is done in this stage (by role)

- Required outputs: what artifacts/fields must exist before exit

- SLA: how fast the stage must move (ex: 24–72 hours)

- Exit criteria (Pass/Fail): what qualifies to move forward vs reject/park

#### 3) Add “handoffs” explicitly

Example:

- Originator → Ops: lead captured + initial notes + owner contact verified

- Ops → Screening (Biz/RE): pre-screen packet ready

- Biz/RE → Ops: pass/fail decision + missing items list

- Ops → Partner workflow: partner selected + intro terms confirmed + intro email sent

#### 4) Add “exception paths”

- Incomplete docs: what happens (Parked stage, follow-up cadence, auto-close time)

- Unresponsive owner: recycle rules

- Partner non-response: partner follow-up cadence + alternate partner decision

#### Expected Outcome (Definition of Done)

✅ SOP exists as a single PDF/Doc that:

- Has stage definitions + pass/fail for every stage

- Has required outputs that match what your CRM will store

- Names the responsible role for each action

- Includes an SLA table (even if simple)

#### “Finished MVP” looks like

If I ask “What happens after Pre-Screen Pass?” you can point to one page that shows:

- who does what,

- what must be produced,

- how long it takes,

- and what “done” means.

## B) Build the infrastructure

### Configure the CRM pipelines (Owners / Originators / Partners / Deals) with required fields, stages, and activity tracking

#### Build Instructions (MVP)

You are building four pipelines, but you want one Deal record to be the “spine” that everything attaches to.

#### 1) Pipelines (minimum viable)

- Deals pipeline (primary)

- Owners pipeline (linked to Deal)

- Originators pipeline (talent + performance)

- Partners pipeline (capacity + responsiveness)

#### 2) Deals pipeline stages (match SOP)

- Intake → Pre-Screen → Screen/Validate → Packaging → Partner Intro → Partner Process → Closed/Won → Closed/Lost → Parked

#### 3) Required fields (minimum viable)

Deal core

- Deal ID (auto or manual standard)

- Owner name + contact

- Asset type + location

- Originator (assigned)

- Deal stage

- Next action + due date (MANDATORY)

- Deal notes (latest update at top)

- Screening decision (Pass/Fail/Park) + reason

- Partner selected + intro date

- Fee expectation (placeholder is fine at MVP)

- Data room link

Owner

- Authority (decision maker? yes/no)

- Objective (sell/refi/raise/capital stack/etc.)

- Timing (0–30 / 30–90 / 90+)

- Responsiveness score (simple: High/Med/Low)

Originator

- Start date, agreement signed (yes/no)

- Activity counts (calls, connects, qualified leads)

- Status (Recruiting / Active / Paused / Removed)

Partner

- Partner type (regulated partner category)

- Fits which deal types

- Intro terms signed (yes/no)

- SLA responsiveness (last response date)

- Status (Active / Dormant / Do Not Use)

#### 4) Activity tracking rules (non-negotiables)

- Every Deal must have:

  - Owner

  - Originator

  - Stage

  - Next action + date

- No stage changes without updating:

  - “Last update note”

  - “What’s blocking it?” (dropdown)

- Any call/email must be logged OR summarized in the Deal note (MVP version).

#### Expected Outcome (Definition of Done)

✅ You can open the CRM and see:

- A Deals board with stage counts

- Each deal has a next action date

- Each originator has an activity summary

- Each partner has status + responsiveness

#### “Finished MVP” looks like

In a meeting, you can filter instantly:

- “Show me deals stuck in Screen > 7 days”

- “Show me originators with 0 activity this week”

- “Show me partners who haven’t responded in 5 days”

### Set up a secure doc intake/upload workflow (structured folders + naming standards)

#### Build Instructions (MVP)

Choose one system (Google Drive / SharePoint / Dropbox)—MVP is fine.

#### 1) Folder structure (simple + scalable)

Top level:

- /ACG Deals/

  - /YYYY/

    - /DealID - OwnerLastName - AssetCity/

      - 01 Intake

      - 02 NDA + Mandate

      - 03 Financials

      - 04 Legal + Entity

      - 05 Asset Docs

      - 06 Packaging

      - 07 Partner Comms

      - 99 Archive

#### 2) Naming standard (must be written and enforced)

DealID_DocType_YYYY-MM-DD_v1
Examples:

- ACG-0021_NDA_2026-01-21_v1.pdf

- ACG-0021_RentRoll_2026-01-22_v2.xlsx

#### 3) Intake method (MVP)

- Owner/originator uploads via:

  - single upload link OR

  - email → ops saves into folder (MVP acceptable but less ideal)

- Ops maintains a Doc Checklist (simple sheet or CRM checklist field).

#### 4) Permissions (MVP security)

- Only ACG core team has access to /ACG Deals/

- Partners only get exported brief + limited shared link (not full drive access)

- Executed agreements stored in a locked “Executed” subfolder

#### Expected Outcome (Definition of Done)

✅ Every deal has:

- A folder created within 24 hours

- A data room link attached in CRM

- A checklist showing what’s missing

- No “random” filenames or duplicates floating around

#### “Finished MVP” looks like

If a partner asks for the Asset Brief and supporting docs, Ops can deliver in 5 minutes with confidence it’s current.

## C) Formalize relationships

### Draft/complete Originator Contractor Agreement + Program Rules

#### Build Instructions (MVP)

- Produce two files:

  - Agreement (comp + term + confidentiality + non-circumvention)

  - Program Rules (behavior + allowed language + boundaries + process)

Operational requirement: originator can’t be “Active” in CRM until signed.

#### Definition of Done

✅ Doc exists, ready for signature, stored in /Originators/Executed/ and logged in CRM.

### Draft/complete Partner Intro Terms

#### Build Instructions (MVP)

One 1–2 page terms sheet that covers:

- Intro purpose + confidentiality

- Non-circumvention

- What triggers fee (definition of “close” / success event)

- Dispute handling (simple)

- Term and survival clause

Operational requirement: no “Partner Intro” stage allowed unless terms are accepted (checkbox in CRM).

#### Definition of Done

✅ Every partner in “Active” status has Intro Terms on file.

### Package Owner NDA / Mandate packet for consistent use

#### Build Instructions (MVP)

Create a “packet” that always goes out the same way:

- NDA

- Mandate/engagement (or your asset owner agreement)

- Short “What happens next” one-pager (process + timeline + what we need)

Operational requirement: Deal cannot move beyond “Pre-Screen” without NDA (or a documented exception rule).

#### Definition of Done

✅ One PDF bundle + one email template + stored in /Templates/Owner Packet/

## D) Make it measurable

### Create the weekly metrics snapshot

#### Build Instructions (MVP)

Create a one-page weekly report (PDF or Doc) generated manually at first.

Include:

- Pipeline counts by stage (Deals)

- Movement this week (entered/exited each stage)

- Bottlenecks (deals stuck > SLA)

- Originator activity (calls, conversations, qualified leads)

- Partner status (active partners, responsiveness, intros sent)

- Top 10 next actions (who owns what by date)

#### Definition of Done

✅ Every Monday (or chosen day), there is:

- A saved snapshot file in /Reporting/Weekly/

- A 30-minute agenda that matches the snapshot

#### “Finished MVP” looks like

Weekly huddle becomes mechanical:

- 10 min: review bottlenecks

- 10 min: assign unblock actions

- 10 min: originator + partner performance

No guessing, no “where is that file,” no vague next steps.

## Quick “Day 10 Acceptance Test”

If all answers are “yes,” Ops MVP is done:

- Can we process a lead from intake → screening → packaging → partner intro without inventing new steps?

- Does every deal have a Deal ID, stage, owner, originator, next action date?

- Does every deal have a folder and naming standard followed?

- Are originator + partner terms ready and in a signature workflow?

- Can you produce a weekly report in <30 minutes that is accurate?

## Business / Real Estate (Screening discipline, deal standards, packaging)

### Role Mission (10-day MVP)

By Day 10, Biz/RE makes ACG credible and consistent: every opportunity is screened the same way, fast-failed quickly when it should be, and packaged into a partner-ready brief that partners can act on without back-and-forth.

#### “Finished MVP” looks like this (vision)

- An originator submits an owner lead → Biz/RE can qualify or fast-fail in 15–30 minutes using a standard checklist.

- A “Pass” means something precise: the deal has the minimum data + docs and a clean story.

- A partner intro happens only when the deal is truly partner-ready: Asset Brief + Data Room + Deal Thesis + Clear asks are complete.

- Originators stay in their lane. Biz/RE protects quality and compliance by controlling what’s asked, promised, and interpreted.

### MVP Deliverables (what this person must produce)

- Owner/Asset Eligibility Criteria (a one-page matrix + CRM checklist)

- Red Flags + Fast-Fail Rules (a one-page list aligned to stages)

- Partner-Ready Standard (minimum data/doc checklist + “missing items” rules)

- Asset Brief Template (2–3 pages) + Typical Deal Path One-Pager

- 3 Example Profiles (Strong / Borderline / Reject) using the templates

- Conversation Boundary Guide (Originator-allowed vs ACG-only)

## A) Define what qualifies

### Lock the Owner/Asset eligibility criteria (asset types, size bands, income/occupancy expectations, authority/objective requirements)

#### Build Instructions (MVP)

Create a 1-page Eligibility Matrix with “Accept / Maybe / Reject” thresholds. Keep it simple enough to train originators, strict enough to protect partner time.

#### 1) Asset Type Fit (set your MVP lane)

Define exactly which asset types are in-bounds for MVP. Example structure:

- In-Bounds (MVP focus): (e.g., multifamily, self-storage, industrial, retail centers, etc.)

- Conditional: (e.g., land, hospitality, special-use, development)

- Out-of-Bounds: (anything you are not packaging in MVP)

MVP rule: fewer asset types = faster screening discipline.

#### 2) Size Bands (choose ranges partners actually care about)

Pick two bands:

- Sweet Spot: where you want most deals to land

- Minimum Floor: below which you generally don’t pursue (unless strategic)

You can express size as:

- Estimated value range (ballpark)

- NOI range

- Units / square footage

- Loan size (if relevant)

#### 3) Performance Expectations (quick indicators)

Define minimum expectations for:

- Occupancy / utilization (if stabilized asset)

- Income documentation available (rent roll, T12/operating statement)

- Stability: how many months of consistent performance

#### 4) Owner Requirements (authority + objective)

Define screening “must haves”:

- Authority: “Is the person we’re speaking to able to decide or sign?”

- Objective: clear intent (sell / refinance / recap / raise / restructure)

- Timeline: immediate / 30–90 / 90+

- Motivation clarity: why now?

#### 5) Turn it into a CRM checklist

Your eligibility matrix must become:

- A checkbox/dropdown set in the Deal record

- A Pass/Fail field with reason codes

#### Expected Outcome (Definition of Done)

✅ One-page Eligibility Matrix that:

- States in-bounds asset types

- Has size bands (sweet spot + minimum floor)

- Defines minimum performance/documentation expectations

- Includes owner authority + objective requirements

- Can be used to decide: Pass / Park / Reject quickly

#### “Finished MVP” looks like

A new lead arrives and within 30 minutes Biz/RE can say:

- “This is in our MVP lane / not in our lane”

- “This is partner-viable / not partner-viable”

- “Here’s what’s missing to proceed”

### Build the red-flag list + “fast fail” rules aligned to screening stages

#### Build Instructions (MVP)

Create a Fast-Fail Sheet with two categories:

#### Category 1: “Instant Reject” (no further work)

Examples of what typically belongs here:

- Owner can’t verify ownership or authority

- Refuses NDA but wants sensitive guidance/data

- Material inconsistencies in basic facts (address, ownership, asset type)

- Legal/ethical red flags (fraud indicators, unwillingness to provide basic proof)

- Asset type is out-of-bounds for MVP

#### Category 2: “Park Until Fixed”

Examples:

- Missing basic docs but owner is cooperative

- Timing too far out (e.g., 6–12 months)

- Financials unclear but can be clarified with T12/rent roll

- Cap stack complexity that requires partner consult later

#### Align to stages

Map fast-fails to where they occur:

- Pre-Screen fast-fails: identity, authority, asset in-bounds, basic objective, baseline data

- Screen/Validate fast-fails: inability to validate income/occupancy, title/ownership issues, critical missing docs, contradictory info

- Packaging fast-fails: owner won’t cooperate with packaging, refuses required disclosures, can’t produce core docs

#### Expected Outcome (Definition of Done)

✅ One-page red-flag list with:

- “Instant Reject” rules

- “Park until fixed” rules

- Stage mapping (where each fast-fail triggers)

- Reason codes that match the CRM (so reporting is clean)

#### “Finished MVP” looks like

Team stops wasting cycles:

- Bad deals get rejected politely fast

- “Maybe later” deals get parked with a clear re-entry trigger

## B) Standardize what “partner-ready” means

### Define the minimum required data/doc standard before partner introduction

#### Build Instructions (MVP)

Create a Partner-Ready Checklist with three layers:

#### Layer 1: Minimum Viable Data (no exceptions)

- Asset address + description

- Asset type + basic specs (units/SF, year built, condition notes)

- Ownership/entity name (or proof path)

- Owner objective + timeline

- High-level financial snapshot (NOI/revenue estimate range is fine if sourced)

- Known issues (vacancy, deferred maintenance, liens—if disclosed)

#### Layer 2: Minimum Viable Docs (target list)

For income-producing assets, MVP docs commonly include:

- Rent roll (or occupancy summary)

- Trailing 12 / operating statement (even if owner-generated initially)

- Tax bill / assessment (baseline)

- Photos / basic condition notes

- Entity/ownership verification (as available)

If a doc is missing, you need a rule:

- Either “partner-ready cannot proceed without it”

- Or “proceed if X substitute exists” (e.g., bank statements in lieu of T12)

#### Layer 3: Deal Story & Ask (required narrative)

Every partner intro must include:

- What the owner wants (one sentence)

- Why it makes sense (one paragraph)

- What ACG is asking the partner to do (clear action request)

- The “next step” call ask (15–30 min review call, etc.)

### Expected Outcome (Definition of Done)

✅ A Partner-Ready Checklist that:

- Defines “minimum viable” data + docs

- Defines substitutes and exceptions

- Defines intro-ready narrative requirements

- Becomes a gating checklist inside CRM

#### “Finished MVP” looks like

Partners get intros that feel professional:

- Fewer follow-ups

- Faster “yes/no”

- More trust in ACG packaging discipline

### Create the Asset Brief template (2–3 pages) and the “Typical Deal Path” expectations one-pager

### Asset Brief Template (2–3 pages) — Build Instructions (MVP)

Design for speed and clarity. Target: 10–20 minutes to assemble once data exists.

Page 1: Executive Snapshot

- Deal ID + asset name/location

- Owner objective + timeline

- Asset overview (type, size, highlights)

- Financial headline numbers (revenue/NOI/occupancy; clearly labeled as “owner-provided” if so)

- ACG view: “why this is worth a look” (3 bullets)

- The ask: “What we want the partner to do next” (1–2 bullets)

Page 2: Asset & Performance Detail

- Unit/SF mix or tenant overview (as applicable)

- Occupancy trend (simple)

- Expenses snapshot (high-level)

- Capex/deferred maintenance notes

- Market context (2–4 bullets, no deep research needed in MVP)

Page 3 (optional): Risks + Process + Attachments

- Key risks / unknowns (bullet list)

- Open questions (what partner should evaluate)

- Data room contents list (what’s included)

- Contact protocol (who communicates with owner and how)

### Typical Deal Path One-Pager — Build Instructions (MVP)

This is for owner alignment and partner clarity. Include:

- The stages (intake → pre-screen → validate → package → partner intro → partner process → close)

- Typical timeline ranges (best case / normal)

- What the owner must provide (docs + responsiveness expectations)

- What ACG does vs what the partner does

- Important disclaimers (plain-English)

#### Expected Outcome (Definition of Done)

✅ Two polished templates exist:

- Asset Brief (2–3 pages) in Doc/PDF format

- Typical Deal Path one-pager
…and both are stored as the single source of truth for packaging.

#### “Finished MVP” looks like

Any team member can pick up the templates and produce consistent outputs that “look like ACG.”

## C) Calibrate quality

### Produce 3 example profiles: Strong / Borderline / Reject

#### Build Instructions (MVP)

Using the new templates, create 3 sample deal profiles (fictionalized is fine, or sanitized real patterns):

#### 1) Strong Example

- Clean authority + clear objective

- Docs mostly available

- Metrics fall in the sweet spot

- Easy partner-ready story

#### 2) Borderline Example

- Some missing docs, but cooperative owner

- Slightly outside sweet spot (size, occupancy, condition)

- Shows how to “Park until fixed” OR how to proceed with conditions

#### 3) Reject Example

- Triggers fast-fail rules

- Demonstrates the polite rejection language + CRM coding

Each example must include:

- Eligibility matrix result

- Fast-fail / pass rationale

- Partner-ready checklist status

- Asset Brief (even if shorter)

#### Expected Outcome (Definition of Done)

✅ Three examples exist that:

- Teach the standards

- Make gray areas obvious

- Can be used to onboard originators + internal team

#### “Finished MVP” looks like

When someone argues “this seems fine,” you can point to examples and say:

- “This is Borderline; it needs X”

- “This is Reject because it triggers rule Y”

## D) Set role boundaries

### Write the Originator-allowed vs ACG-only conversation boundary guide

#### Build Instructions (MVP)

Create a 1–2 page boundary guide with two columns:

### Originator Allowed (what they can gather)

- Basic owner info + best contact method

- Basic asset description (type, address, size/unit count)

- Owner objective + timeline (high-level)

- Whether docs exist (yes/no) and willingness to share under NDA

- Permission to send NDA + intro packet

- Scheduling a call with ACG

### ACG-only (what originators must NOT do)

- Discuss pricing/fees in detail beyond approved language

- Make promises about outcomes, partners, timelines, or approvals

- Interpret financials, underwriting, valuation, token terms, securities-like language

- Negotiate terms

- Request sensitive documents without the approved intake process

- Communicate “partner names” prematurely or attempt direct partner coordination

### Add “safe language” snippets

Include a few approved phrases originators can use:

- “ACG will review and confirm fit after NDA and basic intake.”

- “We don’t make commitments until the core team validates the package.”

- “We’ll introduce you to the right regulated partner if it qualifies.”

#### Expected Outcome (Definition of Done)

✅ Boundary guide exists and is enforced:

- Included in Originator Field Pack

- Signed acknowledgment (checkbox in CRM or as part of Program Rules)

#### “Finished MVP” looks like

Originators act as disciplined scouts, not closers:

- They gather just enough to qualify

- They protect the brand and keep ACG in control of partner-facing accuracy

## Day 10 Acceptance Test for Role 2 (Biz/RE)

If all are “yes,” this role’s MVP is complete:

- Can we decide Pass/Park/Reject in <30 minutes using a standard matrix?

- Do we have written fast-fail rules and stage alignment?

- Do we have a partner-ready checklist that gates intros?

- Can we produce a clean 2–3 page Asset Brief within 1 hour once docs exist?

- Do we have Strong/Borderline/Reject examples for training?

- Do originators have a clear boundary guide with safe language?

## Sales Management (Recruiting, coaching, cadence, performance)

### Role Mission (10-day MVP)

By Day 10, Sales Management makes ACG repeatable on the front end: a real recruiting funnel is running, originators know exactly what to say and do, leads are handled with speed and consistency, and performance is visible weekly.

#### “Finished MVP” looks like this (vision)

- You can point to a live recruiting board and say: “We have 38 targets, 14 in conversation, 5 scheduled, 3 onboarding.”

- Every originator uses the same talk tracks, sends the same approved emails, and follows the same next-step closes.

- Leads don’t die in inboxes: every lead gets assigned, actioned, advanced, recycled, or closed out under a known rule.

- Weekly, the channel improves because you’re tracking inputs (activity) and outputs (qualified deals), and coaching is tied to data.

### MVP Deliverables (what this person must produce)

- Recruiting Funnel (25–50 targets + outreach sequence + tracking board)

- Originator Pitch (script + one-pager version)

- Originator Field Pack (openers, voicemails, emails, objections, closes)

- Lead Handling Workflow (assignment rules, SLAs, recycle rules + enforcement)

- Weekly Cadence System (huddle agenda + stalled-deal recovery + KPI accountability)

- Pilot Onboarding for 2–3 originators end-to-end (validated + refined)

## A) Build the originator channel

### Create a target list + outreach sequence and run a recruiting funnel (25–50 targets)

#### Build Instructions (MVP)

#### 1) Define the “originator ICP” (one paragraph)

Write a simple filter so you don’t recruit everyone:

- Experienced relationship builders (real estate services, commercial brokers, capital introducers, insurance/financial services, M&A adjacent, business consultants)

- Strong communication and professionalism

- Comfortable prospecting owners and booking calls

- Will follow process and boundaries

#### 2) Create the target list (25–50)

Minimum columns:

- Name

- Category (broker / consultant / investor network / etc.)

- Location

- Source (referral, LinkedIn, event, etc.)

- Contact info

- Warmth (warm / medium / cold)

- Notes (why they fit)

MVP standard: mix of

- 10–15 warm (people you or the network already know)

- 10–20 medium (local aligned professionals)

- 5–15 cold (strategic reach)

#### 3) Build an outreach sequence (5–7 touches / 10 days)

You need a sequence you can execute without thinking:

Touch 1 (Day 1): Short email + text (if allowed)
Touch 2 (Day 2): Call + voicemail
Touch 3 (Day 4): Follow-up email with one-pager
Touch 4 (Day 6): Call + “permission close”
Touch 5 (Day 8): Case-style message (“here’s what originators get”)
Touch 6 (Day 10): Breakup email (“should I close your file?”)

Track every touch in the recruiting board / CRM.

#### 4) Set recruiting conversion gates (stage definitions)

Pipeline stages for recruiting:

- Target Identified

- Contacted

- Responded

- Discovery Scheduled

- Discovery Completed

- Offer / Invite

- Onboarding (Agreement + training)

- Active

#### Expected Outcome (Definition of Done)

✅ A live recruiting funnel exists with:

- 25–50 targets loaded

- A defined 5–7 touch sequence in writing

- At least 10+ first touches completed

- Tracking that shows stage counts and next actions

#### “Finished MVP” looks like

At any time you can answer:

- Who’s next to contact today?

- Who’s stalled and why?

- Who is ready to onboard this week?

### Write the Originator Pitch (why join, how supported, how paid, expectations)

#### Build Instructions (MVP)

Create two versions:

#### Version 1: 60-second spoken pitch (verbatim script)

It must include:

- What ACG is (in one sentence)

- What the originator does (simple)

- What ACG provides (support + packaging + partner network)

- How they get paid (high-level, non-confusing)

- What it takes to win (activity + discipline + boundaries)

- The close: “Are you open to a 20-minute overview?”

#### Version 2: One-pager pitch (for email attachment)

Sections:

- Who it’s for

- What you do

- What ACG does

- What you earn (high-level)

- Tools/training/support

- Expectations + boundaries

- Next steps

MVP rule: keep comp explanation clean and avoid anything that triggers compliance risk or overpromising.

#### Expected Outcome (Definition of Done)

✅ Pitch exists as:

- A 60-second script

- A one-pager PDF

- A 3-paragraph email version

#### “Finished MVP” looks like

Every originator hears the same story, and recruiting doesn’t depend on improvisation.

## B) Operationalize execution

### Produce the Originator Field Pack

#### Build Instructions (MVP)

Field Pack should be a single folder + a single “quickstart” doc.

Include:

#### 1) Call openers (3 variations)

- Warm intro

- Cold intro

- Referral intro

Each opener must end with a specific next step:

- “Can we schedule a quick 10-minute call to see if this is worth an NDA + intake?”

#### 2) Voicemail scripts (2 variations)

- “Short and confident”

- “Curiosity + credibility”

#### 3) Email templates (minimum 5)

- Owner intro

- NDA send

- Intake follow-up

- Re-engage stalled owner

- “Not a fit” polite close

#### 4) Objection handling (top 10)

Examples:

- “Is this a scam?”

- “What’s it cost?”

- “I’m not selling.”

- “Send me info.”

- “I’m too busy.”

- “Why do you need documents?”

- “Who are your partners?”

- “What do you do exactly?”

- “How long does it take?”

- “I already have someone.”

Each objection needs:

- a 1–2 sentence response

- a redirect question

- a next-step close

#### 5) “Next step” closes (5)

- NDA close

- Schedule ACG call close

- Document request close

- “Permission” close

- “Park it for later” close

#### Expected Outcome (Definition of Done)

✅ Field Pack exists as a ready-to-issue kit that:

- A new originator can use same-day

- Contains scripts + templates + objections

- Uses only approved language/boundaries

#### “Finished MVP” looks like

Originators stop asking “what should I say?” and start executing.

### Define the lead handling workflow (assignment rules, SLAs, recycle rules) and enforce it

#### Build Instructions (MVP)

#### 1) Assignment rules

Define how leads are assigned:

- Round robin OR by territory OR by originator specialty

- Who can reassign and under what conditions

#### 2) SLA rules (non-negotiable)

Example MVP SLAs:

- New lead contacted within 24 hours

- NDA sent within 24 hours after interest confirmed

- Intake follow-up within 48 hours

- No lead sits without a “next action date” in CRM

#### 3) Recycle rules

Define when a lead is recycled:

- No contact after 3 touches → recycle to “Nurture”

- Owner says “not now” → park with re-engage date (30/60/90)

- Originator inactivity → leads reassigned after X days

#### 4) Enforcement mechanism

- Weekly review of SLA breaches

- “Three strikes” for repeated non-compliance (coaching → probation → remove)

#### Expected Outcome (Definition of Done)

✅ A written Lead Handling SOP exists that includes:

- Assignment method

- SLAs

- Recycle rules

- Reassignment triggers
…and the workflow is reflected in CRM fields/stages.

#### “Finished MVP” looks like

No lead is lost due to sloppiness; pipeline reflects reality.

## C) Establish rhythm

### Launch the weekly cadence: pipeline huddle agenda + stalled-deal recovery + KPI accountability

#### Build Instructions (MVP)

#### 1) Weekly pipeline huddle (30–45 min) agenda

- 5 min: scoreboard (KPI snapshot)

- 10 min: stage bottlenecks (stuck deals)

- 10 min: next-actions review (top 10 priorities)

- 10 min: originator performance + coaching focus

- 5 min: commitments for next week

#### 2) Stalled-deal recovery process (simple playbook)

For any deal stuck > SLA:

- Identify blocker code (docs, owner unresponsive, unclear objective, etc.)

- Choose recovery action:

  - “Re-engage script”

  - “Escalate to ACG call”

  - “Park with next date”

  - “Close out”

#### 3) KPI accountability (MVP KPIs)

Track:

- Inputs:

  - calls made

  - conversations

  - NDAs sent

  - intakes completed

- Outputs:

  - qualified leads passed to ACG screen

  - partner-ready packages created (later stage)

  - intros sent (later stage)

#### Expected Outcome (Definition of Done)

✅ Weekly meeting exists on calendar with:

- A consistent agenda

- KPI snapshot reviewed

- Commitments recorded

- Follow-ups assigned

#### “Finished MVP” looks like

The channel becomes coachable because you can see the numbers and fix the bottleneck.

## D) Pilot the system

### Onboard 2–3 pilot originators end-to-end to validate the workflow and refine scripts

#### Build Instructions (MVP)

#### 1) Choose pilot originators intentionally

Pick:

- 1 warm, experienced relationship-builder

- 1 mid-level learner who will follow process

- (optional) 1 cold recruit to validate pitch strength

#### 2) Onboarding checklist (end-to-end)

- Agreement signed + program rules acknowledged

- 30-minute orientation:

  - what we do / don’t do

  - boundaries

  - workflow + CRM expectations

- Field Pack issued

- First call roleplay (15 minutes)

- First outreach day scheduled

- First weekly huddle attendance

#### 3) Validate through “first 10 conversations”

For each pilot:

- review the first 10 conversations

- refine scripts based on real objections and confusion points

- track early conversion rates:

  - conversation → NDA

  - NDA → intake

  - intake → pass to screen

#### Expected Outcome (Definition of Done)

✅ 2–3 originators are:

- Signed

- Trained

- Active in CRM

- Producing real activity logs
…and you have a list of script/process refinements.

#### “Finished MVP” looks like

You’ve proven the channel can run, and you now know what to adjust before scaling past 10+ originators.

## Day 10 Acceptance Test for Role 3 (Sales Management)

If all are “yes,” Sales MVP is complete:

- Do we have 25–50 recruiting targets loaded into a funnel?

- Is there a defined outreach sequence and has it been executed for at least 10+ targets?

- Do we have a pitch script + one-pager that converts to scheduled calls?

- Do originators have a complete Field Pack they can use without improvising?

- Do we have written lead handling rules + SLAs + recycle rules and are they enforced?

- Have 2–3 pilot originators been onboarded and started producing activity logs?

- Is the weekly huddle running with KPI review and stalled-deal recovery?

## Communications (Collateral, messaging control, trust-building)

### Role Mission (10-day MVP)

By Day 10, Communications makes ACG trusted and repeatable: everyone (ACG core + originators) speaks the same language, sends the same assets, avoids risky phrasing, and can move owners/partners through the process with clarity and confidence.

#### “Finished MVP” looks like this (vision)

- An originator can say, “I’ll send you our overview + NDA,” and it’s one link with the correct, current documents.

- Owners understand the process in 3 minutes: what happens next, what’s needed, and what ACG does vs what the regulated partner does.

- Partners receive consistent, clean packaging: who ACG is, what standards ACG applies, and how intros are handled.

- Messaging is controlled: there’s a single approved language guide and a short “phrases to avoid” list that prevents misrepresentation, overpromising, or accidental securities-ish language.

### MVP Deliverables (what this person must produce)

- Master Messaging & Compliance-Safe Language Guide

- Owner Education Kit

- Originator Program One-Pager

- Partner Onboarding/Intro Pack

- Email Template Library (owner intro, NDA send, intake follow-up, partner intro, originator recruiting)

- Version-controlled “Source of Truth” distribution folder + governance rules

## A) Control the message

### Create the Master Messaging & Compliance-Safe Language Guide

(approved phrases, phrases to avoid, disclaimers)

#### Build Instructions (MVP)

Create a 2–4 page guide that includes:

#### 1) “What ACG is / is not” (one paragraph each)

- ACG is: a screening + packaging + introduction engine that routes qualified opportunities to appropriate regulated/operating partners (worded plainly).

- ACG is not: a broker-dealer, lender, legal advisor, tax advisor, or anyone making commitments on behalf of a partner.

(Keep it factual and simple.)

#### 2) Approved message spine (the 5–7 lines everyone repeats)

Example spine you can operationalize:

- “We help owners get organized and properly presented to the right execution partner.”

- “We run a structured screening process.”

- “If it qualifies, we introduce you to the right regulated/operating partner to execute.”

- “Nothing is promised until screening is complete and the executing partner confirms fit.”

- “We protect your information through NDA and controlled document handling.”

#### 3) Approved phrases (copy/paste)

Create a list of 15–25 “approved phrases” originators and ACG can use. Include:

- Setting expectations (“If it qualifies…”, “Typical timeline depends on…”, “Next step is…”)

- Handling docs (“We’ll share a secure upload link after NDA…”, “Minimum items we need are…”)

- Protecting boundaries (“I’m not able to discuss terms—our team will cover that after screening.”)

#### 4) Phrases to avoid (hard “no” list)

Create a list of 15–25 prohibited phrases that create risk:

- Overpromising (“guaranteed,” “approved,” “we can get you funded,” “we have investors ready”)

- Acting as the executing party (“we’ll underwrite,” “we’ll issue terms,” “we’ll close this”)

- Securities-ish language if you’re not fully covered for it (“investment opportunity,” “token offering,” “we’re selling equity,” “returns,” “ROI guarantees,” etc.)

- Anything implying regulated status you don’t have (“we’re your broker,” “we’re placing capital,” etc.)

#### 5) Disclaimers (short, usable)

Create 3 disclaimer blocks that can be appended in emails / one-pagers:

- General role disclaimer (what ACG does/doesn’t do)

- No commitment disclaimer (screening required, partner decides)

- Confidentiality / NDA reminder

MVP rule: disclaimers must be short enough that people will actually use them.

#### Expected Outcome (Definition of Done)

✅ One PDF/Doc exists that:

- Defines ACG’s role clearly

- Contains approved phrasing + prohibited phrasing

- Includes 3 ready-to-paste disclaimers

- Is referenced inside every kit (footer: “Messaging governed by Master Guide vX.X”)

#### “Finished MVP” looks like

If you listen to any originator call or read any email, it sounds like one company and stays inside safe boundaries.

## B) Build the kits

#### 1) Owner Education Kit

(plain-English explainer, process steps, timeline, FAQs)

#### Build Instructions (MVP)

Deliver as a 3–6 page PDF (plus optional 1-page “quick view”).

Must include:

- What ACG does (plain English, 6th–8th grade readability)

- The process (steps) (Stage-gate simplified into 5–7 steps)

- What we need from you (doc checklist + response expectations)

- Typical timelines (best-case / normal / delayed + why delays happen)

- Confidentiality (NDA, limited sharing, how docs are handled)

- FAQ (10–15 questions)

MVP content standards

- No jargon

- No “big promises”

- Strong emphasis on “screening first → intro second → partner executes”

#### Expected Outcome (Definition of Done)

✅ A single Owner Kit PDF exists that:

- Can be sent to any owner without explanation

- Includes doc checklist and “what happens next”

- Includes FAQs that reduce back-and-forth

#### “Finished MVP” looks like

Owners stop asking basic questions and start completing NDA + intake faster.

#### 2) Originator Program One-Pager

(what it is, who it’s for, benefits, expectations)

#### Build Instructions (MVP)

Make it a true one-pager (tight and scannable). Sections:

- Who it’s for (originator ICP)

- What originators do (2–3 bullets)

- What ACG provides (training, screening discipline, partner routing, templates)

- How you get paid (high-level, clean, no confusion)

- Expectations (activity, CRM hygiene, boundaries)

- What you cannot do (boundary highlights)

- Next step (apply / schedule onboarding call)

#### Expected Outcome (Definition of Done)

✅ One-page PDF exists that:

- Sales Management can attach to recruiting outreach

- Matches the Master Messaging Guide

- Makes expectations unmistakable

#### “Finished MVP” looks like

Recruiting becomes easier because candidates self-select faster.

#### 3) Partner Onboarding/Intro Pack

(ACG overview + how ACG screens/packages + intro protocol)

#### Build Instructions (MVP)

Deliver as a 5–10 page PDF (or a short deck export).

Must include:

- ACG overview (what you are, what you do, what you’re not)

- Screening discipline (stages + fast-fail mentality + partner-ready standard)

- Packaging outputs (Asset Brief, data room, minimum docs)

- Intro protocol (who is on the intro, what is shared, how follow-ups happen)

- Confidentiality + non-circumvention posture (high level)

- Operating rhythm (response expectations, SLAs, status updates)

#### Expected Outcome (Definition of Done)

✅ Partner pack exists that:

- Sets confidence that ACG won’t waste their time

- Makes the intro process predictable

- Aligns with Partner Intro Terms language (at a high level)

#### “Finished MVP” looks like

Partners respond faster because they trust the packaging discipline and protocol.

## C) Standardize outreach

### Draft and store email templates

(owner intro, NDA send, intake follow-up, partner intro, originator recruiting)

### Build Instructions (MVP)

Create a template library where each template includes:

- Subject line options (3)

- Body (short + medium versions)

- Attachments / links (which kit + which doc)

- Required disclaimer block (copy/paste)

- Next-step CTA (one clear ask)

### Minimum set (MVP = 5 templates)

- Owner introduction (from originator)

- NDA send (with owner kit link)

- Intake follow-up (missing items reminder + scheduling close)

- Partner intro (ACG → partner, includes asset brief + link)

- Originator recruiting (pitch + one-pager + CTA)

Operational rule (MVP):

- Templates must explicitly tell the sender what to attach/link.

- Every template must match the Master Guide language.

#### Expected Outcome (Definition of Done)

✅ A single “Templates” folder exists that includes:

- 5 templates with short + medium versions

- Standard disclaimer blocks

- Version label (v1.0)

#### “Finished MVP” looks like

No one writes emails from scratch; everyone sends consistent messages and CTAs.

## D) Make it easy to distribute

### Package everything into a clean version-controlled folder structure (one “source of truth” kit set)

#### Build Instructions (MVP)

Set up a single distribution hub. MVP can be Google Drive/SharePoint + simple versioning.

## Folder structure (recommended MVP)

/ACG_SourceOfTruth/

- /00_Governance/

  - Change Log (simple sheet)

  - Owner: who can edit what

- /01_Messaging/

  - Master Messaging Guide (PDF)

  - Approved Phrases (doc)

- /02_Kits/

  - Owner Education Kit (PDF)

  - Originator One-Pager (PDF)

  - Partner Pack (PDF)

- /03_Templates/

  - Email Templates (doc)

  - Call/voicemail scripts (if comms owns them)

- /04_Logos_Brand/

  - Logos, colors, fonts (MVP)

- /05_Archive/

  - Older versions (read-only)

### Versioning standard (simple)

- File naming: ACG_[Asset]_[Name]_v1.0_2026-01-21.pdf

- Only one folder is “current”: /01–04 are current, /05_Archive holds old.

### Governance rules (MVP must-have)

- One person owns final edits (Comms lead)

- Weekly version cut (e.g., every Monday)

- “Emergency edits” allowed but must update the change log

#### Expected Outcome (Definition of Done)

✅ One link exists that everyone uses as the source of truth, with:

- Clean folders

- Consistent filenames

- Current vs archived separation

- Change log

#### “Finished MVP” looks like

If someone asks, “Which owner kit is current?” the answer is always: “The one in SourceOfTruth → Kits.”

## Day 10 Acceptance Test for Role 4 (Communications)

If all are “yes,” Comms MVP is complete:

- Do we have a Master Messaging & Compliance-Safe Language Guide with approved + prohibited phrasing and usable disclaimers?

- Do we have an Owner Education Kit that explains the process + timeline + FAQs + doc checklist clearly?

- Do we have an Originator Program One-Pager that recruits the right people and sets expectations/boundaries?

- Do we have a Partner Onboarding/Intro Pack that explains ACG screening discipline and intro protocol?

- Do we have 5 core email templates with subject options + CTA + disclaimer blocks?

- Is everything packaged in a single source-of-truth folder with version control and a change log?